## Slide 1: Agile - Scrum
SurendraKC

## Slide 2: Limitations of the Waterfall Model
Waterfall follows a linear sequential approach. Once a phase is done, you cannot go back.
Inflexibility to change – difficult to accommodate new requirements.
Late testing – issues found very late in the cycle.
Delayed customer feedback – customers see the product only at the end.
Risk of project failure if early assumptions are wrong.
Documentation-heavy – less focus on working software.
Not suitable for dynamic environments.

## Slide 3: Introduction to Agile
Agile is a modern software development approach emphasizing flexibility, collaboration, and rapid delivery.
Focuses on iterative development, continuous feedback, and customer satisfaction.
Encourages cross-functional teams and adaptive planning.
Manifested through Agile Manifesto (2001) with 4 core values and 12 principles.
Core Values of Agile:
  Individuals and interactions over processes and tools
  Working software over comprehensive documentation
  Customer collaboration over contract negotiation
  Responding to change over following a plan

## Slide 4: Core Values of Agile
Individuals and Interactions over Processes and Tools
  Agile prioritizes people, communication, teamwork, and quick collaboration rather than depending too much on tools or strict processes.
Example
  A QA finds a bug during testing. Instead of logging it in Jira and waiting for formal approval, the QA directly talks to the developer and gets it fixed quickly.
  A team prefers daily stand-up discussions to solve blockers instead of relying heavily on email or documentation.
Value: Human communication solves problems faster than rigid procedures.
Working Software over Comprehensive Documentation
  The main goal is to deliver working, usable software—not spending too much time creating long documents.
Example
  Instead of writing a 50-page requirement document, the team delivers a working prototype in the first sprint and gathers customer feedback.
  A product increment is tested and available for demo even if all documents are not fully written, as long as key notes exist.
Value: Customers get real value only when the software works, not from thick documents.

## Slide 5: Core Values of Agile
Customer Collaboration over Contract Negotiation
  Agile encourages continuous communication with customers and stakeholders instead of rigidly sticking to the contract.
Example
  After building the first part of a feature, the customer wants a slight UI change. The Agile team discusses and adjusts without saying “It’s not in the contract.”
  Regular sprint reviews help the customer see the product and request changes early.
Value: Working closely with customers ensures the product meets real needs.
Responding to Change over Following a Plan
  Agile accepts and welcomes changes—even late in development. Plans are important, but adapting quickly is more important.
Example
  The team planned to build Feature A in Sprint 2, but a high-priority customer issue arises. The team adjusts and works on the new requirement.
  If market conditions change or a competitor releases something new, the product backlog is reordered accordingly.
Value: Flexibility helps teams deliver what is truly needed, not just what was planned months ago.

## Slide 6: 12 Principles of Agile
Customer Satisfaction through Early and Continuous Delivery
  Principle: Deliver valuable software frequently to keep customers happy.
  Example: A SaaS team releases new features every 2 weeks instead of waiting 6 months, ensuring customers get usable updates quickly.
Welcome Changing Requirements, Even Late
  Principle: Agile embraces change, even late in development.
  Example: An e-commerce team changes the checkout workflow after customer feedback, even though development is mid-way.
Deliver Working Software Frequently
  Principle: Deliver functional software in short cycles (weeks rather than months).
  Example: A mobile app team releases a minimum viable feature, then iterates based on user feedback every 2 weeks.

## Slide 7: 12 Principles of Agile
Business and Developers Must Work Together Daily
  Principle: Continuous collaboration ensures shared understanding and faster decision-making.
  Example: A product manager sits with developers to clarify user stories during daily stand-ups.
Build Projects Around Motivated Individuals
  Principle: Empowered teams are more productive and creative.
  Example: A dev team is trusted to choose the technology stack for a new feature, improving motivation and ownership.
Face-to-Face Conversation is the Best Form of Communication
  Principle: Direct communication reduces misunderstandings and speeds up work.
  Example: A remote team uses video calls to clarify requirements instead of long email chains.

## Slide 8: 12 Principles of Agile
Working Software is the Primary Measure of Progress
  Principle: Progress is measured by working, usable software, not documentation.
  Example: A feature demo at the end of each sprint shows tangible progress rather than just planning documents.
Agile Processes Promote Sustainable Development
  Principle: Teams should maintain a steady pace without burnout.
  Example: Developers work 40-hour weeks consistently rather than sprinting with overtime every release.
Continuous Attention to Technical Excellence and Good Design
  Principle: Quality and maintainability improve speed over time.
  Example: A team implements refactoring and unit tests regularly to avoid messy code that slows future development.

## Slide 9: 12 Principles of Agile
Simplicity – Maximize Work Not Done
  Principle: Focus on what adds value and avoid unnecessary work.
  Example: Instead of building a full reporting module upfront, deliver the most-used reports first.
Self-Organizing Teams Generate the Best Architectures and Designs
  Principle: Teams empowered to make decisions create better solutions.
  Example: Developers choose the optimal microservice architecture instead of following a rigid blueprint from management.
Regular Reflection and Adjustment
  Principle: Teams reflect on how to improve and adapt their processes regularly.
  Example: During sprint retrospectives, a team identifies that code reviews take too long and decides to pair program for efficiency.

## Slide 10: Introduction to Agile
Agile is about mindset, not just process.
Scrum provides a structured yet flexible framework for success.
Focus on people, collaboration, transparency, and continuous improvement.
Success depends on discipline, feedback, and adaptability.

## Slide 11: Agile Frameworks Overview
Agile is an umbrella term for multiple frameworks:
  Scrum – Most popular, team-based iterative approach.
  Kanban – Visual flow management using boards.
  XP (Extreme Programming) – Focus on engineering practices.
  Lean – Eliminates waste, maximizes value.
  SAFe (Scaled Agile Framework) – For enterprise-level Agile adoption.

## Slide 12: Scrum Overview
Scrum is a lightweight Agile framework for managing complex product development.
Based on empirical process control: transparency, inspection, and adaptation.
Uses short iterations called Sprints (usually 2–4 weeks).
Each Sprint delivers a potentially shippable product increment.

## Slide 13: Scrum

## Slide 14: Scrum Workflow Explained
Inputs → Product Owner
  Scrum starts with inputs from customers, team members, managers, executives.
  The Product Owner (PO) collects all these inputs and converts them into work items such as:
    New features
    Enhancements
    Bug fixes
    Technical requirements
  These go into the Product Backlog.

## Slide 15: Scrum Workflow Explained
Product Backlog
  The Product Owner maintains a prioritized, ordered list of everything the product needs.
  Examples:
    Login feature
    Fix API timeout bug
    Add payment method
    UI improvements
  Important: The PO prioritizes based on business value.
Sprint Planning Meeting
  The Team + Product Owner + Scrum Master meet to plan the next sprint.
  During Sprint Planning:
    The team looks at the top items from the Product Backlog.
    The team chooses how much work it can commit to deliver in the upcoming sprint.
    This selected work becomes the Sprint Backlog.
  Sprint Backlog: A list of user stories selected for the sprint.

## Slide 16: Scrum Workflow Explained
Sprint Backlog → Task Breakdown
After selecting user stories:
  The team breaks each story into tasks.
  Example:
    User story: “Add product to cart”
    Tasks:
      Create API endpoint
      Build UI
      Write test cases
  These tasks form the Sprint Backlog that the team will work on.

## Slide 17: Scrum Workflow Explained
2–4 Week Sprint Cycle
The team now starts the Sprint, which lasts 1 to 4 weeks (common: 2 weeks).
Key rules:
  The sprint duration is fixed.
  The scope for the sprint does not change.
  Only the team can decide whether they can add or remove items.
The picture shows this with the big loop arrow.

## Slide 18: Scrum Workflow Explained
Daily Stand-up Meeting (24-Hour Cycle)
Every day, the team meets for 15 minutes to discuss:
  What did I do yesterday?
  What will I do today?
  What blockers do I have?
Purpose: To ensure the team stays aligned and issues are removed quickly.
The Scrum Master facilitates these meetings.

## Slide 19: Scrum Workflow Explained
Burn Down / Burn Up Chart
During the sprint:
  The Scrum Master updates the Burndown chart.
  It shows how much work is completed vs how much is remaining.
  Helps track progress toward the sprint goal.
Sprint Review
At the end of the sprint:
  The team demonstrates the completed work to the Product Owner and stakeholders.
  Feedback is collected.
  This helps refine the Product Backlog.
  This is shown by the team presenting work in the image.

## Slide 20: Scrum Workflow Explained
Finished Work
The work delivered in the sprint is:
  Fully developed
  Fully tested
  Potentially shippable
Shown on the right side as Finished Work (box).
  This becomes part of the product.
Sprint Retrospective
After the sprint review, the team meets internally to discuss:
  What went well
  What didn’t go well
  What can be improved in the next sprint
Outcome:
  Action items for continuous improvement.

## Slide 21: Summary
Product Owner gathers and prioritizes ideas → Product Backlog
Team selects work → Sprint Planning
Work is broken into tasks → Sprint Backlog
Sprint begins (1–4 weeks)
Daily stand-up every 24 hours
Scrum Master ensures process + tracks burndown
End of sprint → Finished Work
Sprint Review with stakeholders
Sprint Retrospective with team
Cycle repeats with next Sprint

## Slide 22: Scrum Roles
Scrum has 3 core roles:
Product Owner (PO):
  Defines product vision and goals.
  Manages the Product Backlog.
  Prioritizes features and represents stakeholders/customers.
Scrum Master (SM):
  Facilitates the Scrum process.
  Removes impediments and ensures team follows Agile principles.
  Acts as a servant leader for the team.
Development Team:
  Cross-functional group (developers, testers, designers).
  Self-organizing and responsible for delivering Sprint goals.

## Slide 23: Product Owner (PO)
Role
  The Product Owner is responsible for maximizing the value of the product and managing the Product Backlog.
Responsibilities
  Defines the vision (e.g., “Allow users to order food from local restaurants easily”).
  Creates and prioritizes user stories in the Product Backlog (e.g., login feature, restaurant listing, payment integration).
  Communicates with stakeholders (marketing team, restaurant partners, investors).
  Decides what gets built first based on business value.

## Slide 24: Product Owner (PO)
The Product Owner decides that the first Sprint should focus on:
User registration and login
Basic restaurant list display
“As a user, I want to sign up with Google or email so I can quickly access the app.”

## Slide 25: Scrum Master (SM)
Role
  The Scrum Master acts as a facilitator and coach for the team. They ensure that Scrum principles are followed and remove obstacles.
Responsibilities
  Conducts Scrum ceremonies: Daily Stand-up, Sprint Planning, Review, Retrospective.
  Removes impediments (e.g., a developer is blocked due to missing API documentation).
  Helps the team improve processes and stay self-organized.
  Shields the team from external distractions.
Example (QuickBite App)
  During Sprint 2, the developers face a delay because the API team hasn’t provided endpoints for restaurant data.
  The Scrum Master arranges a quick sync meeting between the mobile and API teams to resolve it.

## Slide 26: Development Team
Role
  The Development Team builds the working product increment at the end of each Sprint.
Responsibilities
  Selects work items for the Sprint (from backlog).
  Designs, codes, tests, and delivers working features.
  Participates in Sprint ceremonies.
  Ensures quality and integration across components.
Example (QuickBite App)
  During Sprint 3, the Development Team commits to:
  Implementing “Add to Cart” and “Checkout” functionality.
  Testing payment gateway integration.
  At the end of the Sprint, they demo the working app in the Sprint Review.

## Slide 27: Scrum Events (Ceremonies)
Scrum has 5 key events:
Sprint:
  Time-boxed iteration (2–4 weeks).
  Goal: deliver a usable product increment.
Sprint Planning:
  Defines Sprint Goal and items to be completed.
  Involves PO, SM, and Dev Team.
Daily Scrum (Stand-up):
  15-minute daily meeting.
  Each member answers:
    What did I do yesterday?
    What will I do today?
    Any blockers?

## Slide 28: Scrum Events (Ceremonies)
Sprint Review:
  Held at end of Sprint to demonstrate completed work.
  Stakeholders provide feedback.
Sprint Retrospective:
  Reflects on what went well, what didn’t, and how to improve.

## Slide 29: Sprint
Purpose
The Sprint is the heart of Scrum. It’s a fixed timebox (1–4 weeks) during which the team develops a working, usable product increment.
Example: Mobile Banking App
  Let’s assume your team has planned a 2-week Sprint to develop:
  “Login functionality”
  “View account balance”
Activities within a Sprint
  All other events (Planning, Daily Scrum, Review, Retrospective) occur within this Sprint.
  The team works only on items defined in the Sprint Backlog.
  No changes that endanger the Sprint Goal are made.
Output
  A potentially shippable product increment, e.g.:
  Users can log in securely and see their account balance.

## Slide 30: Sprint Planning
Purpose
  To define what can be delivered in the Sprint and how that work will be achieved.
Participants
  Product Owner (defines priorities)
  Scrum Master (facilitates)
  Development Team (plans execution)
Example
  Product Owner shows the top items in the Product Backlog:
  Login with mobile number (high priority)
  Account balance view
  Fund transfer setup
Team discussion:
  Developers assess effort → Login (5 story points), Balance View (8 points)
  They commit to these two as achievable in 2 weeks.
  They define a Sprint Goal:
  “Enable users to securely log in and view their account balance.”
Output
  Sprint Goal
  Sprint Backlog (list of selected backlog items)
  Initial plan for development

## Slide 31: Daily Scrum (Daily Stand-up)
Purpose
  A 15-minute daily meeting for the Development Team to inspect progress and plan for the next 24 hours.
Participants
  Development Team (mandatory)
  Scrum Master and Product Owner (optional observers)
Outcome
  Team synchronizes and identifies blockers early — Scrum Master helps remove them (e.g., get security approval quickly).

## Slide 32: Sprint Review
Purpose
  Held at the end of the Sprint to inspect the increment and gather feedback from stakeholders.
Participants
  Scrum Team (PO, SM, Dev)
  Stakeholders (clients, managers, users)
Example
  At the end of 2 weeks:
  The team demos the new login and balance features.
  Stakeholders test and give feedback:
    “Can we add biometric login in future Sprints?”
    “Add last login time on dashboard.”
Product Owner updates the Product Backlog accordingly:
  Adds “Biometric login” as a new feature for next Sprints.
Output
  Updated Product Backlog (with stakeholder feedback)
  Improved understanding of customer needs

## Slide 33: Sprint Retrospective
Purpose
  To reflect on the past Sprint and identify ways to improve team collaboration, tools, or process.
Participants
  Entire Scrum Team
Example
  After the Sprint Review, the team meets privately:
What went well?
  Daily Scrums helped communication.
  Login module delivered on time.
What didn’t go well?
  Test environment was set up late.
  API documentation was unclear.
Improvements for next Sprint:
  Prepare test environment before Sprint.
  Improve API documentation using Swagger.
Output
  Action items for process improvement (carried into next Sprint)

## Slide 34: The 3 Pillars of Scrum
1. Transparency
  Everyone involved in the project must have a clear and shared understanding of the work, goals, progress, and process. All key aspects of the product and process should be visible and understandable.
Purpose:
  Transparency prevents misunderstandings and ensures all stakeholders have the same expectations.
How Scrum ensures it:
  Use of Product Backlog, Sprint Backlog, and Definition of Done (DoD).
  Daily Scrum and Sprint Review meetings keep progress visible.

## Slide 35: The 3 Pillars of Scrum
2. Inspection
  Regularly check progress toward the sprint and product goals to detect any deviations or issues early.
Purpose: Helps the team identify problems before they grow — ensuring continuous improvement.
How Scrum ensures it:
  Daily Stand-up: Team inspects progress and blockers daily.
  Sprint Review: The completed increment is inspected with stakeholders.
  Retrospective: Team inspects how they worked and what can be improved

## Slide 36: The 3 Pillars of Scrum
3. Adaptation
  After inspection, the team adjusts the plan, tools, or approach to improve outcomes.
Purpose: To ensure the product and process continuously improve and respond to change.
How Scrum ensures it:
  Backlog Refinement: Adjust priorities based on user feedback or market needs.
  Sprint Retrospective: Adjust team processes for efficiency.
  Next Sprint Planning: Modify plans based on what was learned.

## Slide 37: Scrum Artifacts
Product Backlog:
  Ordered list of all desired features, maintained by PO.
  Constantly updated based on feedback.
Sprint Backlog:
  Subset of Product Backlog items chosen for a specific Sprint.
  Owned by the Development Team.
Increment:
  The working, potentially shippable product at the end of the Sprint.
  Must meet the Definition of Done (DoD).

## Slide 38: Scrum Objectives
Deliver working software frequently.
Enable collaboration and transparency.
Emphasize customer satisfaction.
Encourage continuous improvement.
Respond quickly to change.
Foster self-organization and accountability.

## Slide 39: Agile Metrics & Measurements
1. Velocity:
  Measures work completed in a Sprint.
  Helps in future Sprint planning.
2. Sprint Burndown Chart:
  Tracks remaining work vs. time.
  Visual representation of progress toward Sprint Goal.
3. Release Burndown Chart:
  Tracks progress across multiple Sprints toward a release.
4. Lead Time & Cycle Time:
  Lead Time: Time from request to delivery.
  Cycle Time: Time from starting work to delivery.
5. Cumulative Flow Diagram (CFD):
  Visualizes workflow stability and bottlenecks.
6. Escaped Defects:
  Measures defects found after release.
7. Team Happiness / Satisfaction Index:
  Gauges morale and engagement.

## Slide 40: Agile Life Cycle
Concept – Identify need, feasibility.
Inception – Build initial team, define vision.
Iteration / Construction – Develop product incrementally.
Release – Deliver working product to customer.
Maintenance – Support and enhance product.
Retirement – End-of-life phase when product is no longer needed.

## Slide 41: Benefits of Agile/Scrum
Faster time to market.
Better product quality.
High customer involvement.
Improved team morale and ownership.
Flexibility to adapt to change.
Continuous feedback and improvement.

## Slide 42: Challenges in Agile
Resistance to change.
Lack of management support.
Poor backlog management.
Inadequate team collaboration.
Misunderstanding of Agile principles.
Over-commitment during Sprints.

## Slide 44: Kanban – Working Explained
Kanban is a visual workflow management method used to improve flow, reduce bottlenecks, and deliver work continuously.
It works on three main ideas:
  Visualize the work
  Limit work in progress (WIP)
  Improve flow continuously

## Slide 45: Kanban – Working Explained
A Kanban board usually has columns like:
  To Do
  In Progress
  Review
  Done
Teams place work items on cards and move them across the board as work progresses.
Example
  A QA team has a Kanban board:
  A bug card is placed in To Do
  When a developer starts fixing it → moved to In Progress
  When QA tests it → moved to Testing
  After verification → moved to Done

## Slide 46: Kanban – Working Explained
Limit Work in Progress (WIP Limits)
Kanban sets maximum items allowed in each column to avoid overload and bottlenecks.
Example
  If In Progress has a WIP limit of 3:
  The team cannot start new jobs until one of the 3 moves forward.
  This ensures focus, quality, and faster delivery.
Manage and Improve Flow
Teams monitor cycle time (how long work takes), identify bottlenecks, and continuously improve the flow.
Example
  If many items pile up in the Testing column:
  It signals a bottleneck.
  The team may assign more testers or simplify test steps.

## Slide 47: When to use Kanban?
Support teams
QA teams working on daily bug fixes
Operations / DevOps teams
Any team needing continuous delivery instead of sprints
Short Summary
Kanban = Visual Board + WIP Limits + Continuous Flow
  Shows work clearly
  Prevents overload
  Improves delivery speed and quality
Example: A development team moves tasks from To Do → In Progress → Code Review → Testing → Done, with limits to ensure smooth flow.

## Slide 48: Kanban
Kanban is a visual workflow management method used to manage work efficiently through continuous delivery.
The word “Kanban” is Japanese and means “visual card” or “signal card”.
It originated from Toyota’s manufacturing system in the 1940s, used for Lean production.
In Agile, Kanban helps teams visualize work, limit work in progress (WIP), and improve flow.
Unlike Scrum, Kanban does not have time-boxed iterations (no Sprints). Work flows continuously

## Slide 49: Core Principles of Kanban
Kanban is built on two main principles and six core practices.
Principles
  Start with what you do now
    No need to change your existing process immediately.
    Kanban evolves gradually.
  Pursue incremental, evolutionary change
    Encourage continuous, small improvements instead of radical change.
  Respect current roles and responsibilities
    Kanban doesn’t mandate new roles or titles like Scrum does.
  Encourage acts of leadership at all levels
    Everyone contributes to process improvement — not just managers.

## Slide 50: Core Practices of Kanban
1. Visualize the Workflow
  Use a Kanban Board to show tasks and their progress.
  Example board columns:
    To Do → In Progress → Testing → Done
  Each task is represented by a card (physical or digital).
2. Limit Work in Progress (WIP)
  Restrict the number of tasks allowed in each stage.
  Prevents overloading and ensures focus on finishing work.
  Example:
    “In Progress” column can have only 3 tasks at a time.

## Slide 51: Core Practices of Kanban
3. Manage Flow
  Monitor how work moves across the board.
  Identify and remove bottlenecks.
  Goal: achieve smooth, predictable flow.
4. Make Process Policies Explicit
  Define clear rules for moving tasks between stages.
  Example:
    “A task can move to Testing only after peer review is done.”

## Slide 52: Core Practices of Kanban
5. Implement Feedback Loops
  Hold regular reviews or stand-up meetings to assess flow.
  Example meetings:
    Daily stand-ups, Operations review, Service delivery review.
6. Improve Collaboratively & Evolve Experimentally
  Use data and metrics to identify improvements.
  Encourage the team to experiment and adapt processes.

## Slide 53: Kanban vs Scrum
Aspect | Kanban | Scrum
Iterations | Continuous flow | Time-boxed Sprints
Roles | No fixed roles | Scrum Master, PO, Team
Work Commitments | Pull-based | Sprint-based
Change During Work | Allowed anytime | Not allowed during Sprint
Metrics | Lead/Cycle Time | Velocity, Burndown
WIP Limit | Yes | Indirect (by Sprint capacity)
Slide Title: Kanban vs Scrum Notes:
Summary:
Kanban is flow-based, while Scrum is iteration-based.
Kanban suits operational, support, or maintenance work.
Scrum suits feature-based or product development work.

## Slide 54: Kanban Metrics and Flow Measurements
Lead Time
  Time taken from when a request is made to when it’s delivered.
  Example: Customer requests a feature on Monday, delivered on Friday → Lead time = 5 days.
Cycle Time
  Time taken from when work starts to when it’s completed.
  Example: Work started on Tuesday, finished on Friday → Cycle time = 4 days.
Throughput
  Number of work items completed per time period.
  Example: “Team completed 15 tasks last week.”
Cumulative Flow Diagram (CFD)
  Graph showing number of tasks in each state over time.
  Helps visualize WIP, predictability, and bottlenecks.

## Slide 55: Advantages of Kanban
Visual clarity of workflow
Flexibility – changes can be made anytime
Continuous delivery, no waiting for end of sprint
Reduces waste and bottlenecks
Focus on finishing work (not starting too many)
Data-driven improvement (using metrics like Lead Time)
Easy to adopt without changing existing roles/processes

## Slide 56: Challenges of Kanban
No fixed deadlines → harder to predict release schedules
Requires team discipline to respect WIP limits
May lack structure for teams new to Agile
Risk of tasks stagnating in one column if flow is not managed
Continuous monitoring and collaboration needed

## Slide 57: When to Use Kanban
When work is continuous and not time-boxed (e.g., maintenance, support).
When priorities change frequently.
When the team needs visual clarity and flow optimization.
When the team prefers evolutionary change over strict frameworks.
Examples:
  IT Service Desk managing incident tickets.
  QA Team tracking defects.
  Marketing team managing campaign tasks.
  DevOps team monitoring deployment requests.

## Slide 58: Extreme Programming (XP)
XP (Extreme Programming) is an Agile software development framework that emphasizes technical excellence, continuous feedback, and high-quality code.
Created by Kent Beck in the late 1990s.
Designed for environments with frequent requirement changes and high technical risk.
XP improves software quality and responsiveness to changing requirements through strong engineering practices.

## Slide 59: Key Practices of XP

## Slide 60: Lean Software Development
Lean Agile is a mindset and framework that combines Lean principles (from manufacturing) with Agile values (from software development).
Goal: Deliver maximum value to customers with minimum waste and continuous improvement.
Inspired by the Toyota Production System (TPS) — originally used in manufacturing, then adapted to software and IT.
In Lean Agile, the focus is on:
  Value delivery
  Efficiency
  Empowered teams
  Continuous flow of work

## Slide 61: The Philosophy Behind Lean Agile
Lean Agile focuses on doing more with less, by:
  Understanding what the customer values.
  Eliminating anything that doesn’t contribute to that value.
  Encouraging team empowerment and flow.
  Goal: Deliver the right product, at the right time, with the least effort and waste.

## Slide 62: 7 principles of LEAN

## Slide 63: Lean Agile Process Flow
Identify Value → Understand customer needs.
Map the Value Stream → Identify all steps in delivery.
Create Flow → Eliminate bottlenecks and optimize sequence.
Establish Pull → Let teams pull new work when ready.
Pursue Perfection → Continuously improve every step
Example: A healthcare analytics team:
  Maps their workflow for claim processing.
  Identifies delays in QA testing as a bottleneck.
  Automates regression tests.
  Reduces delivery time from 3 weeks → 1 week.
  Continuously measures improvement.

## Slide 64: Real-World Examples of Lean Agile
Example 1: Toyota (Origin)
  Introduced Just-In-Time (JIT) production.
  Only produce what is needed when it’s needed.
  Inspired the pull-based system in software.
Example 2: Amazon
  Uses continuous deployment and small batch releases.
  Teams deploy thousands of updates daily with automated pipelines.
Example 3: Spotify
  Applies Lean-Agile mindset through Squads, Tribes, and Guilds.
  Focuses on autonomous teams and continuous improvement.
Example 4: Healthcare Analytics
  Team eliminates manual Excel reporting (waste) by building automated dashboards → value delivered faste

## Slide 65: LEAN Explained
LEAN works through 5 main principles:
Identify Value
  Understand what the customer truly needs.
  Example
    A customer needs:
    A fast login process
    Not a complex registration form
    So the team focuses on improving the login speed.

## Slide 66: LEAN Explained
Map the Value Stream
  Visualize all steps from start to delivery
  Identify which steps add value and which do not.
  Example
    Steps to fix a bug:
    Log the bug
    Assign to developer
    Developer checks logs
    Developer waits 2 days for server access → waste
    Fix the bug
    QA tests
  The waiting step is waste and must be removed.

## Slide 67: LEAN Explained
Create Flow
  Ensure the work moves smoothly without interruptions or delays.
  Example
    A team automates code deployment so developers don’t wait for manual approvals. This creates a faster flow of work.
Establish Pull
  Work is done when needed, not pushed unnecessarily.
  Example
    In Kanban, a developer takes a new task only when they finish the current one. No overload, no switching tasks.

## Slide 68: LEAN Explained
Continuous Improvement (Kaizen)
  Teams constantly find small ways to improve.
  Example
    Daily standups identify small wastes:
    Slow testing? → Automate it
    Too many bugs? → Improve code review
    Delayed releases? → Improve CI/CD
  Small improvements → Big impact.

## Slide 69: Types of Waste In LEAN
LEAN removes wastes such as:
  Waiting
  Extra steps
  Rework
  Overproduction
  Unnecessary movement
  Too much inventory
  Unused talent
  Example
    Waiting 3 days for requirement clarification = waste Fix: Product Owner must be available daily.

## Slide 70: LEAN Summary
LEAN = Remove Waste + Deliver Value Faster + Continuous Improvement
Examples in IT:
  Remove waiting → Faster approvals
  Remove rework → Better requirements
  Remove delays → Automate deployments
  Improve flow → Use Kanban
LEAN makes teams faster, efficient, and high-quality.

## Slide 71: SAFe (Scaled Agile Framework)
SAFe (Scaled Agile Framework) is a structured approach that helps large organizations implement Agile at enterprise scale.
It combines Lean, Agile, and DevOps principles to align teams, programs, and portfolios around common business goals.
Designed for enterprises where multiple Agile teams (50–1000+ people) must collaborate and deliver integrated solutions.
Key Objective: Deliver value faster and continuously, across the organization, while maintaining alignment, quality, and governance.
Example: A global healthcare analytics company with 20 Agile teams across departments uses SAFe to align all teams to a single “Enterprise Data Platform” roadmap.

## Slide 72: Why SAFe?
Traditional Agile works well for small teams (5–10 members), but challenges arise at scale:
  Multiple teams working on the same product.
  Dependencies between teams.
  Different priorities and lack of alignment.
  Need for governance, compliance, and strategic planning.
SAFe addresses these by: Synchronizing multiple teams Aligning strategy with execution Ensuring built-in quality and governance Enabling enterprise agility

## Slide 73: Key Events in SAFe
Event | Purpose | Example
PI Planning | Align all teams on goals for the next 8–12 weeks. | Teams plan features for “Patient Data Integration” for next PI.
Iteration Planning | Team-level sprint planning every 2 weeks. | Define sprint backlog.
System Demo | Show integrated work from all teams at end of iteration. | Demo full workflow from frontend to backend.
Inspect & Adapt (I&A) | Reflect and improve processes after each PI. | Identify quality or flow bottlenecks.
Scrum of Scrums (SoS) | Coordination meeting between teams. | Discuss dependencies across ART.
PO Sync | Align Product Owners across teams on priorities. | Ensure consistent backlog refinement.

## Slide 74: Roles in SAFe
Notes:
Team Level
Scrum Master – Facilitates team ceremonies, removes blockers.
Product Owner – Manages team backlog and priorities.
Agile Team – Develops, tests, and delivers working software.
Program Level
Release Train Engineer (RTE) – “Chief Scrum Master” for ART; ensures coordination and flow.
Product Management – Defines vision and prioritizes Program Backlog.
System Architect/Engineer – Defines overall technical vision.
Portfolio Level
Lean Portfolio Management (LPM) – Aligns strategy, budgeting, and execution.
Epic Owners – Manage large-scale business initiatives.

## Slide 75: SAFe Work Artifacts

## Slide 76: SAFe Explained
Define Business Strategy (Portfolio Level)
Leaders set:
  Vision
  Business goals
  Budgets
  Value streams (end-to-end flow of value)
Example: “Build a new digital healthcare platform in 2025.”

## Slide 77: SAFe Explained
Create ARTs (Agile Release Trains)
An ART is a long-term team-of-teams (50–125 people) that delivers value together.
  Includes developers, testers, architects, PO, SM, RTE
  Works on the same mission
  Operates on a fixed calendar (Program Increment)

## Slide 78: SAFe Explained
Build the Program Backlog
The Product Management prepares features for the ART.
Features include:
  Description
  Business value
  Acceptance criteria
Example: “Add online appointment scheduling.”

## Slide 79: SAFe Explained
PI Planning (The Biggest SAFe Event)
Every 8–12 weeks, all teams meet (physically or virtually) to plan the next Program Increment.
Activities:
  Understand the vision
  Break features into stories
  Identify dependencies
  Create team plans
  Commit to PI objectives
Outcome:
  PI Objectives
  Risks (ROAMed)
  Program board

## Slide 80: SAFe Explained
Execute Iterations (Sprints) Within the PI
Teams follow Scrum/Kanban to deliver stories.
Each iteration:
  Iteration Planning
  Daily Standups
  Development + Testing
  Iteration Review
  Iteration Retrospective
Teams demo working features every 2 weeks.

## Slide 81: SAFe Explained
System Demo (End of Every Iteration)
All teams show integrated work to stakeholders.
Purpose:
  Ensure features work end-to-end
  Get fast feedback
Inspect & Adapt (End of PI)
A larger retrospective for the entire ART.
  Includes:
    PI demo
    Quantitative metrics
    Problem-solving workshop
    Improvement action items
Goal: Continuous improvement across the whole organization.

## Slide 82: SAFe Explained
Release Value (On-Demand)
SAFe allows releasing anytime during or after the PI when the work is ready.
Examples:
  Deploy a new feature to customers
  Release an internal tool
Continuous Learning Culture
SAFe promotes:
  Lean thinking
  DevOps
  Continuous delivery pipelines
  Innovation time (IP Iteration)

## Slide 83: SAFe Explained - Summary
Define strategy and value streams
Form Agile Release Trains (ARTs)
Prepare program backlog with features
Conduct PI Planning (plan 8–12 weeks)
Execute sprints and deliver stories
Show integrated work in system demos
Inspect & Adapt at end of PI
Release value on-demand
Continuously improve